## Sheet1
Task | Duration (Hours) | Assigned to | Deadline | Status | Priority | Wks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Days | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91 | 98
Initial and one-off tasks
Initial requirements gathering | 8 | TH | 06/15 | Complete | High
Prep for kick-off workshop | 4 | TH | 06/16 | Complete | Low
Technical site audit | 4 | TH | 06/16 | Complete | High
Project kick-off workshop | 3 | TH | 06/17 | Complete | Medium
Post-workshop documentation | 6 | TH | 06/17 | In Progress | High
Competitor analysis | 5 | AK | N/A | To Do | Medium
Target audience analysis | 8 | AK | N/A | To Do | Medium
Develop content tone of voice guide | 16 | TH | N/A | To Do | Low
Content production templates and setup | 24 | TH | 06/30 | To Do | High
Style guide setup | 32 | TH | N/A | To Do | Low
Onpage optimization
Onpage optimization: site map and robots.txt | 24 | AK | N/A | To Do | Medium
Onpage optimization: update all titles, metas, H1s | 32 | AK | N/A | To Do | Medium
Onpage optimization: site speed optimizations | 32 | AK | N/A | To Do | High
Onpage optimization: internal linking | 32 | AK | 07/14 | To Do | Medium
Content planning
Content planning: keyword research | 40 | TH | N/A | To Do | Medium
Content planning: landing page plan | 24 | TH | N/A | To Do | Medium
Content planning: articles plan | 32 | TH | N/A | To Do | Medium
Link building
Link building: blogger research | 24 | AK | N/A | To Do | Medium
Link building: backlink cleanup | 16 | AK | N/A | To Do | Medium
Link building: blogger outreach | 40 | AK | N/A | To Do | Medium
Link building: guest post plan | 32 | AK | N/A | To Do | Medium
Link building: guest post outreach | 32 | AK | N/A | To Do | Medium
Reporting
Reporting: Decide on reporting template & cadence with client | 2 | AK | 06/30 | To Do | High
Reporting: Deliver first progress report | 4 | AK | 06/30 | To Do | Medium
Reporting: Client presentation | 1 | AK | N/A | To Do | Medium
Reporting: Setup ongoing SEO audits and reporting | 4 | AK | N/A | To Do | Medium